## Shopenzer Testcases
|  |  |  | Date | 2022-10-25
|  |  |  | Team ID | PNT2022TMID42348
|  |  |  | Project Name | smart solutions for railways
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Commnets | TC for Automation(Y/N) | BUG ID | Executed By
1 | Functional | Registration | Registration through the form by Filling in my details |  | 1.Click on register 2.Fill the registration form 3.click Register |  | Registration form to be filled is to be displayed | Working as expected | Pass |  |  |  | Nikhila
2 | UI | Generating OTP | Generating the otp for further process |  | 1.Generating of OTP number |  | user can register through phone numbers, Gmail, Facebook or other social sites and to get oto number | Working as expected | pass |  |  |  | Preethiha
3 | Functional | OTP verification | Verify user otp using mail |  | 1.Enter gmail id and enter password 2.click submit | Username: abc@gmail.com password: Testing123 | OTP verifed is to be displayed | Working as expected | pass |  |  |  | Kishokkumar
4 | Functional | Login page | Verify user is able to log into application with InValid credentials |  | 1.Enter into log in page 2.Click on My Account dropdown button 3.Enter InValid username/email in Email text box 4.Enter valid password in password text box 5.Click on login button | Username: abc@gmail password: Testing123 | Application should show 'Incorrect email or password ' validation message. | Working as expected | pass |  |  |  | Raguram
5 | Functional | Display Train details | The user can view about the available train details |  | 1.As a user, I can enter the start and destination to get the list of trains available connecting the above | Username: abc@gmail.com password: Testing123678686786876876 | A user can view about the available trains to enter start and destination details | Working as expected | fail |  |  |  | Nikhila

## Testscearnios
Test Scenarios
1 | Verify user is able to see login page
2 | Verify user is able to loginto application or not?
3 | Verify user is able to navigate to create your account page?
4 | Verify user is able to recovery password
5 | Veriify login page elements
Search
1 | Verify user is able to search by entering keywords in search box
2 | Verify user is able to see suggestions based on keyword entered in search box
3 | Verify user is able to see related auto suggestions displaying based on keyword entered in search box
4 | Verify user is able to see no matches found message when no results are matching with entered keyword
5 | Verify user is able to see seach detailed page when nothing entered in textbox